## Summary&SetUp
Project Summary
BrainCell Educational Game
Test prerequisites: Populate data from general knowledge api. Create a new player.§§ For each question select yoiur chosen category from the drp down list.
You will need to install
npm install
npm start
database | mongod
mongo
use braincell_db
integration tests | npm install mocha
npm run webdriver-update
npm run webdriver
npm run protractor
Unit tests | https://facebook.github.io/jest/docs/en/tutorial-react.html
https://medium.com/@dfrase/testing-react-with-jest-and-enzyme-20505fec4675
https://github.com/jefflau/jest-fetch-mock#usage
https://gist.github.com/alfonsomunozpomer/de992a9710724eb248be3842029801c8

## UnitTests
Dev_test_ref | Test_Objective | Container | Expected Result | Result
1 | game will have a player | game_container | Unable to start game without a player | Passed
2 | game will have a game status | middle_container | game status will move from 0-3 | Passed
3 | player can have a name | game_container | Player is required to enter name. | Passed
4 | player can select from a list of categories | game_container | AllCategories array will be displayed | Passed
5 | player can select a category | game_container | playerCategories function will be recorded. | Passed
6 | player can change selected a category | quiz_container |  | v2
7 | player can start the game | middle_container | When player starts answering question game will start | Passed
8 | player can pause game | middle_container |  | v2
9 | player can restart game | middle_container |  | v2
10 | player can view question & multiple choice answers | Answer_container | question and multiple choice answers are displayed. | Passed
11 | player can select one answer | Answer_container | Only one answer can be selected | Passed
12 | player will have a level |  | game increments from easy medum hard questions | Passed
13 | player can have the same level across categories |  |  | NA
14 | player can have different levels across catergories |  |  | NA
15 | player can move up a level |  | game increments from easy medum hard questions | Passed
16 | player can stay on the same level |  | NA- requirements change | NA
17 | player can move down a level |  | NA- requirements change | NA

## SystemIntegrationTests
SIT_test_ref | Test_Objective | User | Category | Level | Expected Result | Result
Verify start game
Verify game complete
verify all categories
verify player categories
Verify select category
Verify player results
Verify player result chart

## UserAcceptanceTests
UAT_test_ref | User_Requirement | Test_Steps | User | Category | Level | Expected Result | Result
1 | Verify that a player can enter player name. | Enter name in input box, enter to complete. Check that player name is stored in the database. | a | Geography | easy | player name is displayed on screen and saved in database. | Passed
2 | Verify that a player can select a category from category list. | Select category from the dropdown list. | a | Sport | easy | Randomised sport question will be displayed. | Passed
3 | Verify that each selected category will be removed from the level when answered correctly | Select category from the dropdown list. Check that Geography and Sport cannot be selected. | a | General Knowledge | easy | Randomised General Knowledge question will be displayed. | Passed
4 | Verify that questions from each category are randomised. | replay game repeat order of category selection verify that questions are randomised. | a | all | all | Randomised questions will be displayed | Passed
5 | Verify that multiple choice answers are shuffled on screen. | replay game repeat order of category selection verify that answers are randomised on view on screen. | a | all | all | Answers are visually randmised within boxes on screen | Passed
6 | Verify that a player can move through each level from 0-5, 6-10, 11-15, 16-20 | As the player plays the game check that the player can move from easy to medium and hard questions. | a | all | all | Player can increment through each level collecting points for correct answers. | Passed
7 | Verify that a player can win a maximum of 1000 points. | Answer all questions correct = 1000 points | a | all | all | Max 1000 points for all correct answers | Passed
8 | Verify that a player points total is calculated for each level of question. | Answer only some questions correct and some incorrect = calculated points. | a | all | all | Calculated points displayed | Passed
9 | Verify that a teacher can view each players performance on progress charts | View charts | a | all | all | chart will display player name and score | Passed
9 | Verify that more than player can log in at anytime and play braincell.
10 | Verify that a player can log in to game on a variety of portals mac, laptop, tablet, phone. | na

## DefectTracking
Defect Number | Summary | Description/How To Recreate | Test Results | Priority | Complexity | Assigned to.. | Status | attachments
1 | Remove the category/ refresh categories. Does not refactor the player list. | After investigation the function.splice was removing from allcategories & playercategories (multiple arrays) when it should have been removed from the playerCategories array only. To recreate. Answer 6 questions from game then after the 6th question it will start removing from the array. | Retested after Eds fix. All tests passed- many thanks!!! | medium | high | Ed | Resolved
2 | Question level should follow easy-medium-hard. |  | Retested during code review. Fixed thanks Graeme. | high | medium | Graeme | Resolved
3 | some questions have "special characters" can these be removed please> | test with &#; | Retested, no issues raised. Many thanks. | high | low | Ed | Resolved
4 | Welcome header is in the game container. change to app.js |  | Retested during code review.Thanks Sarah. |  |  | Sarah | Resolved
5 | Exception displayed with double click on hard section | Hard question section. double click on >1 incorrect answer. Exception is displayed. | Rested during code review, no issues raised. Thanks Ed. | low | low | Debbie | Resolved
6 | Number of points should equal 1000 for all correct answers. | Complete game with all correct answers. Total score should match 1000. | Retested, no issues raised. Many thanks. | High | medium | Ed | Resolved.
7 | Category refresh is updating one cell too early. | Play game 1-4 notice that categories are removed but at cell 5 will display all categories. this should be from cell 6. | Retested, no issues raised. Many thanks. | Medium | medium | Graeme | Resolved.